## Use Case 1
Use Case 1: Home Page
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
T1 - 1 | User is not logged in | Verify the application is loading from the link | 1. Open the application through the URL | Application should load and the home page should be displayed | Pass
T1 - 2 | User is not logged in | Verify contents of the navbar. | 1. Open the application through the URL 2. Browse the home page | Verify the five buttons in the navbar: - "Home" - "Services" - "Blog" - "FAQ" - "Contact" Buttons should be located to the top right. Buttons should have a white strip on thop when mouse is on top of them to indicate a selection. | Pass
T1 - 3 | User is not logged in | Verify the copyright footer. | 1. Open the application through the URL 2. Scroll down to the bottom of the page. | Verify the contents of the footer: • Quick links • Contact information • Copyrights Quick links should be located on the bottom left part of the footer. Contact information should be located on the bottom right part of the footer. Copyrights should be under everything at the bottom. | Pass
T1 - 4 | User is not logged in | Verify the "Home" button | 1. Open the application through the URL 2. Click on "Home" button from the right part of the Navbar. | Home page is opened | Pass
T1 - 5 | User is not logged in | Verify the "Services" button | 1. Open the application through the URL 2. Click on "Services" button from the right part of the Navbar. | Services dropdown menu is presented with options. | Pass
T1 - 6 | User is not logged in | Verify the "Blog" button | 1. Open the application through the URL 2. Click on "Blog" button from the left part of the Navbar. | Blog is opened | Pass
T1 - 7 | User is not logged in | Verify the "FAQ" button | 1. Open the application through the URL 2. Click on "FAQ" button from the right part of the Navbar. | FAQ is opened | Pass
T1 - 8 | User is not logged in | Verify the "Contact" button | 1. Open the application through the URL 2. Click on "Contact" button from the right part of the Navbar. | Contact is opened | Pass
T1 - 9 | User is not logged in | Verify the Header of the page. | 1. Open the application through the URL 2. Browse the home page | Header should be displayed at the center. Header should present the website and its goal in a short term. | Fail | Although header is present, there are minor spelling mistakes observed.
T1 - 10 | User is not logged in | Verify the contents of the page - Body | 1. Open the application through the URL 2. Browse the home page | User should be presented with all different plans for viewing - total of 6 (six). | Fail | Although all six plans are displayed, there are minor spelling mistakes observed.
T1 - 11 | User is not logged in | Verify "Why Choose Our Services" | 1. Open the application through the URL 2. Browse the home page | User should be presented with a brief promotional content explaining the advantages of the service. | Pass
T1 - 12 | User is not logged in | Verify "Services We Offer" | 1. Open the application through the URL 2. Browse the home page | User should be presented with a list containing all services offered by the page: • Fast delivery • 24/7 support • High-quality service • Privacy and safety • Our guarantee • Secure payment • Feedback Section | Fail | "High-quality service" is overlapping with 24/7 support
T1 - 13 | User is not logged in | Verify feedback quotes | 1. Open the application through the URL 2. Browse the home page | Section with feedback comments is being displayed. | Pass | Although the section is present and displays as per documentation there isn't a option to add/send feedback as a user. Such functionality should be added.
T1 - 14 | User is not logged in | Verify contents for "How to Buy a Package?" | 1. Open the application through the URL 2. Browse the home page | Section with a step-by-step guide how to buy/purchase a package. | Fail | The background image has overlapping digits that are not an image and they are visible.

## Use Case 2
Use Case 2: Services
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
T2-1 | User is not logged in | Verify functionality of Services buttons - 6 months | 1. Open the application through the URL 2. Move the mouse over "Services" 3. Select "6 Months" 4. Select "Buy 6 months" 5. Click order Now | User should be redirected to the purchase page | Fail | User is redirected back to home page, where the relevant subscription can be purchased and correct redirection is made.
T2-2 | User is not logged in | Verify functionality of Services buttons - VIP commercial | 1. Open the application through the URL 2. Move the mouse over "Services" 3. Select "VIP commercial" 4. Select "Buy VIP commercial" 5. Click order Now | User should be redirected to the purchase page | Fail | User is redirected back to home page, where the relevant subscription can be purchased and correct redirection is made.
T2-3 | User is not logged in | Verify functionality of Services buttons - SUPER VIP COMMERCIAL | 1. Open the application through the URL 2. Move the mouse over "Services" 3. Select "SUPER VIP COMMERCIALs" 4. Select "Buy SUPER VIP COMMERCIALs" 5. Click order Now | User should be redirected to the purchase page | Fail | User is redirected back to home page, where the relevant subscription can be purchased and correct redirection is made.
T2-4 | User is not logged in | Aditional sections appearing when browsing through Services section | 1. Open the application through the URL 2. Move the mouse over "Services" 3. Select any subscription. 4. Move the mouse over "Services" again. 5. Confirm the presence of 3 new services - Buy Youtube/Facebook/Twitter followers. | As per documentation these sections are not supposed to be there. | Fail | This is possibly new functionality that is being implemented.

## Use Case 3
Use Case 3: Blog, FAQ, Contact
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
T3-1 | User is not logged in | Validate Blog contents. | 1. Open the application through the URL 2. Click on the Blog button. | Page should contain fun stories and updates about the website. | Fail | There is an issue with the image not loading for the only blog story updated.
T3-2 | User is not logged in | Validate FAQ contents. | 1. Open the application through the URL 2. Click on the Blog button. | Page should contain Frequently Asked Questions section covering common user queries. | Pass
T3-3 | User is not logged in | Validate Contact US contents | 1. Open the application through the URL 2. Click on the Contact Us button. | Page should contain a form for users to submit contact inquiries. | Fail | "Click here" hyperlink to upload an image does't work. Not linked to any web page.

## Use Case 4
Use Case 4: Accounts
Test Case ID | Prerequisites | Title/Description | Steps | Expected result: | Pass / Fail | Comments
T4-1 | User is not logged in | Validate a succesfull path to create an account. | 1. Open the application through the URL 2. Browse the home page 3. Select a plan - 6 MONTHS 4. Click on Buy now 5. Fill the form with the required information - Full name - Valid email adress - Payment method 6. Agree with T&C 7. Click Place order | Account should be created. | Pass | Accounts are currently being created by a backoffice team. No issues found but this shoud be locked to the customer only in order to create a strong password. | Priority options: | 1. Blocker
T4-2 | User is not logged in | Validate a succesfull log in. | 1. Open the URL to log in: http://webtv.iptvsmarters.com/switchuser.php 2. Click on "Add new playlist" 3. Enter valid login details - Name (display name) - Username (provided by backoffice) - Password (provided by backoffice) - Host | User should be authorised to log in. | Pass | Although journey is working there are some feedback points to adress: • Log in button should be added to the home page. • The "host" field is not properly displayed as it doesnt say Host on it. • There isn't an option to change/reset/recover the password. |  | 2. High
3. Medium
4. Low

## Use Case 5
Use Case 5: Viewing the service
Test Case ID | Prerequisites | Description | Steps | Expected result: | Pass / Fail | Comments
T5-1 | User is logged in | Validate working content | 1. Log in from the relevant login page. 2. Select "Live tv" 3. Select a title to watch. 4. Confirm a working stream. | Content should be available to watch. | Pass
T5-2 | User is logged in | Validate working content | 1. Log in from the relevant login page. 2. Select "Movies" 3. Select a title to watch. 4. Confirm a working stream. | Content should be available to watch. | Pass
T5-3 | User is logged in | Validate working content | 1. Log in from the relevant login page. 2. Select "Series" 3. Select a title to watch. 4. Confirm a working stream. | Content should be available to watch. | Pass
T5-4 | User is logged in | Validate seamless streaming | 1. Log in from the relevant login page. 2. Select "Live tv" 3. Select a title to watch. 4. Watch for at least 10 minutes. | Content should stream without buffering or error messages. | Pass
T5-5 | User is logged in | Validate seamless streaming | 1. Log in from the relevant login page. 2. Select "Movies" 3. Select a title to watch. 4. Watch for at least 10 minutes. | Content should stream without buffering or error messages. | Pass

## BUG REPORTING
Bug Report
Bug ID | Test Case ID | Priority | Severity | Title | Steps to reproduce | Expected result | Actual result | Comments
1 | T1-9 | Medium | Medium | Spelling and grammar mistakes in the header. | 1. Open the application through the URL 2. Browse the home page | The text in the header should be free of spelling and grammar errors. | Spelling and grammar errors observed. | \BUG screenshots\header-bug.png
2 | T1-10 | Medium | Medium | Spelling and grammar mistakes in the subscription plans. | 1. Open the application through the URL 2. Browse the home page | The text in the subscription plans should be free of spelling and grammar errors. | Spelling and grammar errors observed. | \BUG screenshots\plans-bug.png
3 | T1-12 | Low | Low | Overlapping content in Services | 1. Open the application through the URL 2. Browse the home page | The content should be properly aligned in 6 different boxes positioned 3 x 2. | One box overlaps with another. Mis-aligned | \BUG screenshots\services-offered-bug.png
4 | T1-14 | Low | Low | Overlapping content in the background image | 1. Open the application through the URL 2. Browse the home page 3. Press "ctrl + a" to select all elements | The background should be an image and shoudn't contain a text. | Upon selection some elements remain visible. | \BUG screenshots\how-to-buy-bug
5 | T2-1, T2-2, T3-2 | Low | Low | Hidden menus appear in the Services | 1. Open the application through the URL 2. Move the mouse over "Services" 3. Select any subscription. 4. Move the mouse over "Services" again. 5. Confirm the presence of 3 new services - Buy Youtube/Facebook/Twitter followers. | There shoudn't be any extra content that differs from the topic of the website. | New sections appear - buy youtube/facebook/twitter followers. | \BUG screenshots\buy-followers-bug.png
6 | T3-1 | Low | Low | Image not loading on the Blog page. | 1. Open the application through the URL 2. Click on the Blog button. 3. Locate the story "How it work" | Image next to the story should be loading. | Image is not loading. | \BUG screenshots\blog-bug.png
7 | T3-3 | Low | Low | "Click here" hyperlink is not an actual link. | 1. Open the application through the URL 2. Click on the Contact Us button. 3. Locate the "Click here" in the instructions to upload a picture. | "Click here" should be a hyperlink to a image sharing platform. | "Click here" is plain text. | \BUG screenshots\contact-us-bug.png